## Verification & Handover
GREEN STAR BUILDINGS v1.1 - VERIFICATION AND HANDOVER CREDIT SUBMISSION FORM
Outcome: The building has been optimised and handed over to deliver a higher level of performance in operation.
Criteria | Requirement | Submission Question | Compliance (Y/N/NA) | Evidence Provided | Documentation Required
MINIMUM EXPECTATION
Metering and Monitoring | Metering Distribution | Does the building have accessible energy and water metering for all distinct uses and major uses? |  |  | As-built drawings showing location of all energy and water meters
Is metering provided for each separate tenancy or unit?
Is floor by floor metering provided where entire floors have a single use?
| Metering Schedule | Has a metering schedule been provided in accordance with CIBSE TM39? |  |  | Metering schedule
| Metering Attributes | Do all meters provide continual information (up to 1-hour interval readings)? |  |  | Product data sheets demonstrating pattern approval by NMI or recognised standard
|  | Are meters commissioned and validated per NABERS Metering and Consumption Rules? |  |  | Completed metering validation documents
|  | Are meters pattern approved by NMI or recognised standard? |  |  | Product data sheets or certificates
| Automatic Monitoring | Is an automatic monitoring system implemented that reports consumption trends? |  |  | Letter of confirmation from contractor/metering provider
|  | Does the system raise alarms when energy/water use exceeds parameters? |  |  | Extracts from commissioning reports
Commissioning and Tuning | Environmental Performance Targets | Were environmental performance targets documented prior to schematic design? |  |  | Extracts from design intent report or OPR
Does the report include targets for energy use, water consumption, IEQ and airtightness?
|  | Has the building owner signed off on the report/document? |  |  | Signed design intent report or OPR
| Services and Maintainability Review | Was a services and maintainability review conducted prior to construction? |  |  | Evidence of review being conducted
Did the review involve building owner, design consultants, architect, FM, head contractor and ICA?
|  | Were all items addressed, closed-out and documented in Services and Maintainability Report? |  |  | Services and Maintainability Report signed by all parties
| Building Commissioning | Were commissioning requirements included in construction documentation prior to construction? |  |  | Extracts from construction documentation
|  | Was a commissioning plan developed prior to start of commissioning? |  |  | Extracts of commissioning plan
|  | Was commissioning completed per a recognised standard (AIRAH DA27, ASHRAE, CIBSE, SA TA 5342)? |  |  | Extracts from commissioning report
| Airtightness | Were airtightness targets set prior to schematic design based on ATTMA Australia Guide? |  |  | Evidence of how airtightness targets were determined
|  | Was the air barrier system schematic reviewed prior to end of design development? |  |  | Evidence of air barrier system schematic review (marked up drawings)
|  | Was an approach to delivering airtightness developed prior to construction? |  |  | Airtightness testing and commissioning plan
|  | Was airtightness testing carried out per AS/NZS ISO 9972 Method 1 by ATTMA member? |  |  | Building airtightness testing report or ATTMA Green Star Commissioning report
|  | Were test results shared with building owner (regardless of targets being met)? |  |  | Signed confirmation from building owner
|  | Were airtightness test results included in energy modelling? |  |  | Extracts from energy modelling report
| Building Systems Tuning | Has building owner/developer committed to tuning process with quarterly adjustments for 12 months? |  |  | Commitment/contract from building owner and head contractor
|  | Does commitment include a building tuning manual/plan with roles and responsibilities? |  |  | Extracts of building tuning plan
Does the building tuning team include FM, ICA/owner rep, head contractor and relevant subcontractors?
Building Information | Operations and Maintenance Information | Has O&M information been provided to building owner for all nominated building systems? |  |  | Extracts of operations and maintenance information
Does O&M info include maintenance instructions, procedures, schedules, service contacts, warranties and as-built drawings?
Do appropriate user groups have access to information for best practice environmental outcomes?
Does O&M info include guidance on keeping information up to date and validating alerts/faults?
| Building Logbook | Has a building logbook been developed per CIBSE TM31 for all nominated building systems? |  |  | Building logbook
|  | Was the logbook presented to building owner prior to occupation? |  |  | Evidence of provision to building owner
| Building User Information | Has building user information been provided to building owner and FM prior to occupation? |  |  | Building user information
Is the building user information publicly available to intended users?
Is the information communicated in a way easily understood by the target audience?
|  | Is the information in an editable, digital format accessible for updates by FM? |  |  | Evidence of editable format provision
CREDIT ACHIEVEMENT (1 point)
| Pathway Selection | Which pathway is being pursued? (Select one or both if Total Building Services Value > $20m)
Total Building Services Value (if applicable): $_________
[ ] Soft Landings Approach
[ ] Independent Commissioning Agent
[ ] Both (required if Total Building Services Value > $20m)
Soft Landings Approach | CIBSE ANZ Framework Implementation | Have Stages 1 to 4 of the CIBSE ANZ Soft Landings Framework been implemented? |  |  | Evidence of CIBSE ANZ framework implementation
|  | Are sample worksheets from CIBSE ANZ for Stages 1-3 completed? |  |  | Completed worksheets
Are actions for Stage 4 identified?
| FM Team Involvement | Was the FM team (or building owner rep) involved in commissioning and handover process?
Did FM team take part in developing brief technical guide and O&M manual?
|  | Did FM team sign-off on the O&M manual? |  |  | Signed O&M manual
|  | Was FM team trained before handover (including BMS demonstration)? |  |  | Training records
|  | Does FM team have continued access to design/construction team for 2 years post PC? |  |  | Contractual evidence of continued access
Independent Commissioning Agent | ICA Appointment | Was an ICA appointed prior to design development? |  |  | Letter from building owner confirming ICA appointment
| ICA Qualifications | Is the ICA an advocate for and reporting directly to the project owner? |  |  | CV of ICA with qualifications and experience
Is the ICA independent of any consultant/contractor involved in design or installation?
Is the ICA a registered professional engineer or qualified technician with demonstrated commissioning competency?
Does the ICA have experience commissioning at least 2 similar projects?
| ICA Involvement | Did ICA advise, monitor and verify commissioning/tuning throughout design development, tender, construction, commissioning and tuning phases? |  |  | Evidence of ICA involvement from design stage through to tuning
NOTES:
1. Complete all applicable sections based on the performance level being targeted.
2. For Minimum Expectation: All three criteria (Metering and Monitoring, Commissioning and Tuning, Building Information) must be met.
3. For Credit Achievement (1 point): In addition to Minimum Expectation, either Soft Landings Approach OR Independent Commissioning Agent must be met.
4. For projects with Total Building Services Value > $20m: BOTH Soft Landings Approach AND Independent Commissioning Agent must be met for Credit Achievement.
5. Attach all supporting documentation as referenced in the 'Documentation Required' column.
6. Mark Y (Yes), N (No), or NA (Not Applicable) in the Compliance column.